## Estimate
PROJECT TITLE
Steel Cost Adjustment Estimate (for Use During Design)
Quantity of Steel for Estimate for Eligible Items
Enter Lbs. of steel included in the project as listed in GSP 1-09.3.OPT2.FR1
Initial Cost Basis (ICB) | 0.4
Est. Adjustment
Reinforcing Steel (see Specbook 9-07) |  |  |  | Lbs. | X | 0.4 | X | 0.03 | 0
Structural Steel (Specbook 6-03.2) |  |  |  | Lbs. | X | 0.4 | X | 0.03 | 0
Soldier Piles |  |  |  | Lbs. | X | 0.4 | X | 0.03 | 0
Permanent Steel Casings For shafts and borings |  |  |  | Lbs. | X | 0.4 | X | 0.03 | 0
Permanent Steel Casings for concrete Pilings |  |  |  | Lbs. | X | 0.4 | X | 0.03 | 0
Use
|  |  | 0 | [5 empty] | 0
|  | Total = |  | Lbs.
For Adjustment
Estimate Calculation Notes
Estimate for Steel Cost Adjustment, Pay Item 7731 Use in any project with 50,000 lbs. or more of steel
- For the Initial Cost Basis (ICB) use a value of $0.40/lb. If the HQ Construction Office has approved an ICB different than $0.40, unprotect this form and revise the (ICB) below.
- Multiply the pounds of steel by $0.40, i.e. 50,000 Lbs x $0.40 = $20,000
- Multiply the above product by 0.03, i.e. $20,000 x 0.03 = $600*
The bid items that are eligible for steel cost adjustment can include bid items that are entirely composed of steel, e.g., Steel Reinforcing Bar for Bridge. Bid items can also include lump sum items that use significant quantities of steel , such as Superstructure, Lump Sum.
*The 3% used in this calculation is based on potential payout (assuming a 13% increase in the Monthly Steel Material Index Value). For multi-year projects, or projects with large quantities of steel, this percentage can be increased to 5%. Contact the HQ Construction Office to verify changing the percentage.

## Payment
PROJECT TITLE
Steel Cost Adjustment Payment Calculation (for Use During Construction)
How to Use this Calculator
Monthy Calculation Data
| ITEM | QUANTITY | Bid Opening Date:
Date of Calculation:
Payment or Credit Calculation
Get Steel Materials Values
Initial Cost Basis (ICB)
Base Steel Materials Index Value (BV)
Monthly Steel Materials Index Value (MV)
| Pounds of Eligible Steel (WS) |  |  | 0
| Calculated Payment or Credit |  |  | #DIV/0!
CA = Cost Adjustment, dollars
MV = Monthly Steel Materials Index Value from BLS for the month determined above
BV = Base Steel Materials Index Value taken as the most recent value published on the BLS website on the day of bid opening.
ICB = Initial Cost Basis of steel
WS = Weight of steel eligible for cost adjustment
Calculate Payment
1. Enter the Initical Cost Basis (ICB) (Normally this value is $0.40
2. Enter Base Steel Materials Index Value (BV) at the beginning of the project.
( This Number Does NOT get revised )
3. Enter the Monthly Steel Materials Index Value (MV) each month when preparing the monthly Progress Estimate. (Click on the cell below labeled WPUSISTEEL1 to obtain this value.)
4. Enter the eligible pounds of steel (WS) for the monthly Progress Estimate.
This sheet will calculate the dollars of PAYMENT or CREDIT
This is the amount of adjustment to be paid for the month. Note: Only those items included in the contract provisions are eligible for adjustment.
How is the Steel Cost Adjustment determined ?
1. If the MV is within ten-percent of the BV, there will be no adjustment. 2. If the MV is more than 110-percent of the BV, then:
CA = (((MV - BV) ÷ BV) - 0.10) × (ICB × WS)
3. If the MV is less than 90-percent of the BV, then
CA = (((MV - BV) ÷ BV) + 0.10) × (ICB × WS)
WPUSISTEEL1
GSP 1-09.3.OPT2.FR1
Note on B24: WEB LINK for Bureau of Labor Statistice web site to obtain Base and Monthly Steel Materials Index Value: https://data.bls.gov/timeseries/WPUSISTEEL1?include_graphs=false&output_type=column&years_option=all_years
Note on B26: Use a value of $0.40/lb. If the HQ Construction Office has approved an IBC different than $0.40, Enter the approved revised the Initial Cost Basis (ICB) amount.
Note on B27: BASE STEEL MATERIALS VALUE = The Base Steel Materials Index Value (BV) will be the most recent value published on the Bureau of Labor Statistics (BLS) website on the day of bid opening (even if listed as a preliminary value).
Note on B28: MONTHLY STEEL MATERIALS VALUE = The Monthly Steel Materials Index Value (MV) will be the final index value published on the BLS website for any month during the life of the contract.