## Inventory Instructions
Inventory Instructions - PDM #23-06 "Pre-NCHRP 350 Guardrail Terminal Replacment"
1 | ASDE receives request for Pre-NCHRP 350 Terminal inventory from design team.
2 | ASDE sends copy of these inventory instructions to project team. (Note: the inventory instructions have a tab containing instructions on how to use ArcGIS Pro to get the guardrail terminal inventory)
3 | Design team generates an guardrail terminal inventory listing using ArcGIS Pro and exports results to an excel spreadsheet. ▪ Link to instructions on how to use ArcGIS Pro to generate inventory:
| https://wsdot.wa.gov/engineering-standards/design-topics/roadside-safety |  | Under the Guardrail Terminal and Anchor Inventory heading near the bottom of the Tools Templates & Links tab
4 | Design team uses their generated inventory listing to assist them in visually verifying in the field all Pre-NCHRP 350 terminals located within project limits per PDM #23-06 instructions. (Note: Every guardrail terminal found within project limits should be physically checked and identified in the field to determine if they are Pre-NCHRP 350 terminals -- this is regardless if a terminal is shown as a pre-NCHRP 350 terminal in the provided inventory listing or not. The provided inventory listing may be out-of-date and/or contain errors/omissions.)
5 | Design team updates and corrects (if needed) the generated inventory listing and returns it to the ASDE. The ASDE will forward to updated inventory listing to the HQ Design Safety & Innovation Office (Ida’s group). The corrected inventory listing should show the following:
| a) | Add a column to spreadsheet showing how any Pre-NCHRP 350 guardrail terminals located on the project were evaluated. Were they replaced? Were they left in place? If left in place, which waiver condition from the Project Delivery Memo was met?
| b) | Were there any errors in the provided inventory? If yes, the inventory sheet should provide corrections to any inventory errors (for instance – add-in any missing Pre-NCHRP 350 terminals to the inventory, correct any mis-identified terminals and put in correct terminal type, correct any Pre-NCHRP 350 terminal locations, etc.). Any corrections to the inventory listing should have the affected cells highlighted in yellow.
6 | HQ Design Safety & Innovation Office (Ida’s group) updates guardrail terminal inventory by adding in information showing that Pre-NCHRP 350 terminals were evaluated, if they were replaced or not, and correct inventory errors.

## ArcGIS Inventory
Link to: | WSDOT Interchange Drawing Viewer

## Example-Inventory Feedback
OBJECTID | FeatureNumber | RouteIdentifier | EndTreatmentType | AccumulatedRouteMile | PointType | Direction | Side | OffRouteFlag | Pre-NCHRP 350 GR Terminal Evaluation (new column) | RegionName | MaintenanceAreaName | ContractNumber | BCTReplacementFlag | CategoryType | StateRouteMilepost | AheadBackIndicator | LRSYear | AheadBackIndicator | Remarks (new column)
1526 | WSDOT0001285896 | 005 | SRT | 104.5 | S | D | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway mainline | 104.43 | A | 2022 | A
1545 | WSDOT0001262602 | 005 | BCT | 104.206 | S | I | R |  | Replaced with MASH Terminal | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway mainline | 104.14 | A | 2022 | A
7928 | WSDOT0001285896 | 005 | Connection to wall, bridge rail, or other barrier | 104.219 | E | I | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway mainline | 104.15 | A | 2022 | A
7947 | WSDOT0001262602 | 101 | BCT | 365.463 | S | I | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Non-Interstate freeway mainline | 367.309997558594 366.50 | A | 2022 | A | BCT listed at incorrect location
|  | 101 | BCT |  |  | D | R |  | Replaced with MASH Terminal |  |  |  |  | Interstate freeway mainline | 366.9 |  |  | A | Missing BCT added to inventory list
12190 | NEW-895 | 101 | Connection to wall, bridge rail or other barrier | 365.474 | E | I | R |  |  | Olympic Region | Area 1 - Tacoma |  |  |  | 367.32 | A | 2022 | A
19785 | WSDOT0001285897 | 101 | Connection to wall, bridge rail or other barrier | 365.473 | E | I | L |  |  | Olympic Region | Area 1 - Tacoma |  |  |  | 367.32 | A | 2022 | A
19956 | WSDOT0001285891 | 005P110402 | Connection to wall, bridge rail, or other barrier | 0.311 | S | R | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.31 | A | 2022 | A
19957 | WSDOT0001285892 | 005P210402 | Softstop | 0.03 | S | R | R |  |  | Olympic Region | Area 1 - Tacoma | 009392 | S | Interstate freeway ramp (not LX) | 0.03 | A | 2022 | A
19962 | WSDOT0001285899 | 005P210402 | BCT | 0.045 | E | R | R |  | Replaced with Type 11 Anchor | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.05 | A | 2022 | A
19963 | WSDOT0001285900 | 005Q110481 | Connection to wall, bridge rail, or other barrier | 0.002 | S | R | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0 | A | 2022 | A
22360 | WSDOT0001288623 | 005Q110481 | Anchors | 0.076 | E | R | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.08 | A | 2022 | A
22363 | WSDOT0001252629 | 005Q110481 | Anchors | 0.134 | E | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.13 | A | 2022 | A
23329 | WSDOT0001285897 | 005Q110481 | Connection to wall, bridge rail, or other barrier | 0.004 | S | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0 | A | 2022 | A
23498 | WSDOT0001285891 | 005Q210481 | MSKT | 0.015 | S | R | R |  |  | Olympic Region | Area 1 - Tacoma | 009884 | S | Interstate freeway ramp (not LX) | 0.02 | A | 2022 | A
23499 | WSDOT0001354921 | 005Q210481 | Connection to wall, bridge rail, or other barrier | 0.243 | E | R | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.24 | A | 2022 | A
23500 | WSDOT0001285892 | 005R110303 | SRT BCT | 0.197 | S | R | R |  | Did not remove - PDM Waiver #3 | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.2 | A | 2022 | A | BCT incorrectly identified as SRT
23503 | WSDOT0001354921 | 005R110303 | Connection to wall, bridge rail, or other barrier | 0.217 | E | R | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.22 | A | 2022 | A
23506 | WSDOT0001285899 | 005R110435 | Connection to wall, bridge rail, or other barrier | 0.218 | S | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.22 | A | 2022 | A
23507 | WSDOT0001285900 | 005R110435 | Anchors | 0.3 | E | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.3 | A | 2022 | A
25926 | WSDOT0001288623 | 005R110435 | BCT SRT | 0.039 | E | R | R |  | No action - not a BCT | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.04 | A | 2022 | A | (SRT incorrectly identified as BCT)
25929 | WSDOT0001252629 | 005R110459 | Connection to wall, bridge rail, or other barrier | 0.083 | S | R | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.08 | A | 2022 | A
34807 | WSDOT0001335372 | 005R110459 | Buried-In-Backslope | 0.278 | S | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.28 | A | 2022 | A
34808 | WSDOT0001335372 | 005R110459 | Connection to wall, bridge rail, or other barrier | 0.29 | E | R | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.29 | A | 2022 | A
36200 | WSDOT0001335317 | 005R110459 | Connection to wall, bridge rail, or other barrier | 0.29 | E | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.29 | A | 2022 | A
36201 | WSDOT0001335317 | 005S110373 | Buried-In-Backslope | 0.161 | S | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.16 | A | 2022 | A
37133 | WSDOT0001335318 | 005S110373 | Connection to wall, bridge rail, or other barrier | 0.199 | E | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.2 | A | 2022 | A
37135 | WSDOT0001335371 | 005S110373 | Connection to wall, bridge rail, or other barrier | 0.208 | E | R | R |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.21 | A | 2022 | A
37136 | WSDOT0001335371 | 005S210373 | Connection to wall, bridge rail, or other barrier | 0.133 | E | R | L |  |  | Olympic Region | Area 1 - Tacoma |  |  | Interstate freeway ramp (not LX) | 0.13 | A | 2022 | A
NOTE: For Coulmn G: Direction (D) = Decreasing, (I) = Increasing, and (R) = Ramp