## Matrix
Project | [8 empty] | Date:
| Title: | [7 empty] | WIN:
| Route: | [7 empty] | PIN:
| MP(s): | [7 empty] | List any additional PINs at bottom or attached to this form.
Cost:
● | Begin with the list of generic considerations offered below; modify or add entries as required. Indicate if the entry is a Project Delivery Goal by checking/selecting the Goal box; if not, leave blank.
● | Weights: Enter numbers indicating the relative priority of each Project Delivery Goal (checked/selected)―higher numbers are higher priority―1 is the lowest.
● | Ratings: Numbers from 1 to 10, with 1 lowest and 10 highest; a two point range is provided for the generic entries as given. Select the Rating that best fits the specifics of your Project Delivery Goal. If a Goal is modified or rewritten, confirm that the ratings are appropriate and revise them accordingly. Any new Goals added to the Matrix will need to have ratings provided based on the probability of each PDM to meet the Goal.
● | Score: Multiply the selected Rating of each method by the priority Weight for each Goal. Total the scores for each method and compare.
| Consideration |  |  |  |  | Weight | DBB |  |  | DB
[7 empty] | Rating |  | Score | Rating |  | Score
S C H E D U L E |  | Goal | Minimize project delivery time
[7 empty] | 4 | 5 |  | 9 | 10
|  | Goal | Meet a specific critical Milestone or Completion date
[7 empty] | 4 | 5 |  | 9 | 10
|  | Goal | Utilize (federal) funding by a certain date
[7 empty] | 6 | 7 |  | 9 | 10
|  | Goal | Effectively manage weather, environmental and/or other construction windows
[7 empty] | 6 | 7 |  | 9 | 10
|  | Goal | Funding limitations impacts ability to compress the schedule and/or contract all the work early in the process (such as the biennium, grants, etc.)
[7 empty] | 9 | 10 |  | 6 | 7
Goal
Goal
C O S T / F U N D I N G |  | Goal | Minimize project cost
[7 empty] | 6 | 7 |  | 6 | 7
|  | Goal | Complete the project on budget
[7 empty] | 6 | 7 |  | 6 | 7
|  | Goal | Maximize the project scope and improvements within the budget
[7 empty] | 4 | 5 |  | 8 | 9
|  | Goal | Project cost must not exceed a specific amount
[7 empty] | 6 | 7 |  | 8 | 9
|  | Goal | Determine the total project cost as early as possible in the schedule
[7 empty] | 4 | 5 |  | 9 | 10
|  | Goal | Meet 3rd Party requirements with possible impacts in design and construction
[7 empty] | 6 | 7 |  | 4 | 5
Goal
Goal
S T A N D A R D S |  | Goal | Meet or exceed project quality/scope requirements ―utilizing opportunities for innovation
[7 empty] | 6 | 7 |  | 9 | 10
|  | Goal | Owner requires control of design to meet specific design and construction constraints and/or standards (such as aesthetics)
[7 empty] | 8 | 9 |  | 5 | 6
|  | Goal | WSDOT maintains control of specific project elements (such as significant ROW or environmental impacts)
[7 empty] | 8 | 9 |  | 5 | 6
Goal
Goal
F U N C T I O N / I N N O V A T I O N |  | Goal | Minimize maintenance and operations costs (assume maintenance and operations is not part of DB contract)
[7 empty] | 9 | 10 |  | 5 | 6
|  | Goal | Maximize capacity and mobility of improvements
[7 empty] | 6 | 7 |  | 9 | 10
|  | Goal | Minimize impacts to the public and/or local businesses during construction
[7 empty] | 6 | 7 |  | 9 | 10
|  | Goal | Incorporate opportunities for innovation and efficiencies to meet specific requirements
[7 empty] | 4 | 5 |  | 9 | 10
|  | Goal | Avoid or minimize impacts to the project through risk transfer and innovation (such as environmental risks)
[7 empty] | 4 | 5 |  | 9 | 10
|  | Goal | Minimize project permanent area impact (footprint) (This would be project neutral unless the project is larger and more complex―then use the ratings ranges provided)
[7 empty] | 6 | 7 |  | 8 | 9
Goal
Goal
Delivery method indicated by this matrix → → → |  |  |  | _____________ |  |  |  | Totals― | 0 |  |  | 0
Final Project Delivery Method Selected
☐ Design-Bid-Build ☐ Design-Build
Authorization
Project Engineer
| Name: |  |  |  | Signature: | [6 empty] | ______________________________________________
PDE/EM Manager
| Name: |  |  |  | Signature: | [6 empty] | ______________________________________________
Regional Administrator
| Name: |  |  |  | Signature: | [6 empty] | ______________________________________________
Attach project information, assumptions and additional justification to Form